## Sheet1
PROJECT TIMELINE
Client: Mr. Kelvin To
Project; KelReport
Date: 13 July 2013
NO | ITEMS/ DESCRIPTIONS | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
A | Front end | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1 | HTML
2 | Register | bar: Month 1 Week 4 to Month 2 Week 5
Login
Email Subscribe
Search
3 | Home Widget: | bar: Month 1 Week 4 to Month 2 Week 5
+ Featured Posts by Section
+ Related Posts (Next n Latest post)
+ Sections
4 | Site by Country | bar: Month 2 Week 5 to Month 2 Week 7
Multilanguage | bar: Month 2 Week 5 to Month 2 Week 7
5 | Article:
+Default content | bar: Month 2 Week 5
+ Where to buy | bar: Month 2 Week 6
+ Share | bar: Month 2 Week 6
+ Comment | bar: Month 2 Week 7 to Month 2 Week 8
+ Vote: Hate / Buy / Bought | bar: Month 2 Week 7 to Month 2 Week 8
+ Product Gallery | bar: Month 2 Week 5 to Month 2 Week 6
6 | User:
+ Profile | bar: Month 2 Week 5
+ Message -> cancelled
+ Friends | bar: Month 3 Week 9 to Month 3 Week 10
+ Following / Follower | bar: Month 3 Week 9 to Month 3 Week 10
+ Activities | bar: Month 3 Week 10 to Month 3 Week 11
+ Photos | bar: Month 3 Week 11 to Month 3 Week 12
+ Punch list (Liked Products) | bar: Month 3 Week 11 to Month 3 Week 12
+ Badges (Achievement)
B | Back-end
1 | Main CMS | bar: Month 1 Week 1
2 | Article: | bar: Month 1 Week 1 to Month 1 Week 4
+ Article control
+ Multilanguage
+ Sections
+ Product tag
+ Publish Permission
+ Publish time
+ Product Gallery
3 | Product: | bar: Month 2 Week 5 to Month 2 Week 6
+ Tag
+ Thumbnail
+ Store
4 | User: | bar: Month 1 Week 1 to Month 1 Week 4
+ Group Control
+ Permission Control
+ User control
+ Email to member list
+ Export member list
5 | Brand system:
+ Company control
+ Brand control
+ Store control
+ Stats: views by brand, stats by option (Hate, will buy, bought)
6 | Stand-Alone Gallery system: (simplier than the last quotation, up requested by Client)
+ Image gallery | bar: Month 1 Week 1 to Month 1 Week 4
+ Product Gallery | bar: Month 2 Week 5 to Month 2 Week 6
7 | Advertisement System: | bar: Month 4 Week 13 to Month 4 Week 16
+ Advertiser control
+ Zone control
+ Advertisement control:
· Create/upload/edit/delete
· Sale by Impression/Time/CPC
· Stats by Impression/Time/Clicks